## Sheet1
Defect ID | Title | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | State (Status) | Owner (Assigned To) | Project/Iteration | Environment | Attachments | Reported Date | Remarks
DE-1001 | Login button not working on Chrome | Login page button unresponsive when clicked. | 1. Open site in Chrome v118 2. Enter valid credentials 3. Click login | Should redirect to dashboard | Button unresponsive, no action | Critical | High | Open | Dev A | Sprint 3 – Auth Module | Windows 11, Chrome 118 | Screenshot_login.png | 2025-09-21 | To be re-tested after fix
DE-1002 | Cart total not updating after product removal | Cart shows wrong total after removing product. | 1. Add 2 products to cart 2. Remove one product | Cart should update total | Total not updated | Major | High | Open | Dev B | Sprint 4 – E-commerce | macOS, Safari 16 | Screenshot_cart_issue.png | 2025-09-21 | Needs urgent fix
DE-1003 | Payment gateway timeout error | Users receive timeout error while making payment. | 1. Add product to cart 2. Proceed to payment 3. Select credit card 4. Click Pay | Payment should be processed successfully | Timeout error shown after 30 seconds | Critical | High | Open | Dev C | Sprint 5 – Payment Integration | Windows 10, Edge v115 | Payment_error_log.txt | 2025-09-21 | Check payment API timeout settings
DE-1004 | Search results not sorted correctly | Search results appear in random order. | 1. Search for 'Laptop' 2. Observe product listing order | Results should be sorted by relevance or filters applied | Random order displayed | Major | Medium | Open | Dev D | Sprint 6 – Search Module | Linux Ubuntu 22, Firefox 117 | Screenshot_search_order.png | 2025-09-21 | Needs sorting algorithm fix
DE-1005 | Profile picture upload fails | User unable to upload profile picture > 5MB. | 1. Go to Profile Settings 2. Upload 10MB image | System should compress or accept image with warning | Upload fails with no error message | Minor | Low | Open | Dev E | Sprint 7 – User Profile | Android 13 App v4.2 | Profile_upload_issue.mp4 | 2025-09-21 | Add validation for image size